## Roadmap
PromptHalo — SOC 2 Programme Map
Seven workstreams · 42 tasks · 9 milestones. Week numbers are relative to the programme start date in C3. Change that date and every date column moves. Use the +/− outline buttons in the left margin to collapse a workstream. The bar chart to the right is driven by the Start week and End week columns, so editing those redraws it.
Programme start (Monday of week 1) |  | 2026-08-10
ID | Workstream and tasks | Owner | Status | Start wk | End wk | Start date | End date | Controls closed | Note | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
WS1 | Document remediation — Make the 42 edits that close the design gap, and reissue the library clean. | Security Officer | Not started | 1 | 8 |  |  | Retires: CMP-004, CMP-005, GOV-003
| Choose one destination for deficiencies and amend the four cross-references | Security Officer | Not started | 1 | 2 |  |  | CC4.2-03, CC4.2-04, CC4.2-06, CC5.3-04, CC7.5-03
| PLN-ISP and PLN-HRS insertions — 24 of the 26 plan-side edits | Security Officer | Not started | 1 | 3 |  |  | CC1.1-01, CC1.2-02, CC1.5-03, CC2.3-01, CC2.3-05
| POL-RSK-001 five clauses and POL-ISP-001 Annex A reconciliation | Security Officer | Not started | 3 | 5 |  |  | CC3.1-02, CC3.1-05, CC3.3-04, CC3.4-03, CC3.4-04
| POL-NET-001 network diagram clause; POL-IRP-001 §6 role model; POL-BCP-001 §8 alternate | Security Officer | Not started | 4 | 6 |  |  | CC6.6-03, CC7.4-01, CC9.1-04
| AI policy architecture: reduce POL-AI-001 §15/§16 to pointers, delete POL-SDLC-001 §14 | Security Officer | Not started | 5 | 7 |  |  | CC6.3-04, CC8.1-06
| Refresh 21 stale tables of contents, fix seven cross-references, reissue as v1.1 | Security Officer | Not started | 6 | 8 |  |  | CC5.3-01, CC5.3-02
WS2 | Risk programme — Stand the risk process up and run the first full assessment. | Security Officer | Not started | 3 | 11 |  |  | Retires: GOV-004, HR-003, AI-001
| Configure the register to the §10 twelve-field list; seed the CC1.2 independence entry | Security Officer | Not started | 3 | 4 |  |  | CC3.2-03, CC3.2-06
| Apply the §7 scales and §9 treatment bands so scores and due dates compute | Security Officer | Not started | 4 | 5 |  |  | CC3.1-04, CC3.2-01
| First assessment in three sweeps — entity, vendor, AI and agentic | Security Officer | Not started | 5 | 8 |  |  | CC3.2-02, CC3.2-04, CC3.2-07
| Fraud section from §11 including management override and client-access misuse | Security Officer | Not started | 7 | 9 |  |  | CC3.3-01, CC3.3-02, CC3.3-03
| Seven change triggers into engagement and vendor intake | Security Officer | Not started | 8 | 10 |  |  | CC3.4-01, CC3.4-02
| Obligations register and objective-to-control mapping | Security Officer | Not started | 9 | 11 |  |  | CC3.1-03, CC3.1-05
WS3 | Tooling and automation — Turn on the controls a system can operate, so people are left with the 34 that need a person. | Security Officer | Not started | 1 | 12 |  |  | Retires: APP-001, PHY-001, AC-002, AC-003, OPS-002, AI-001
| gitleaks pre-commit and CI; Semgrep in the pipeline — free, and retires APP-001 | Security Officer | Not started | 1 | 1 |  |  | CC6.7-03, CC7.1-02, CC7.1-03
| Audit logging at 13-month retention, GuardDuty in every region, alert on disabling logging | Security Officer | Not started | 2 | 3 |  |  | CC7.2-01, CC7.2-02, CC7.2-03
| Kandji plus company laptops — retires PHY-001 and closes three CC6 controls | Security Officer | Not started | 4 | 6 |  |  | CC6.1-05, CC6.8-01, CC6.8-02
| GitHub Enterprise, branch protection, deployment population export | Security Officer | Not started | 5 | 7 |  |  | CC8.1-04, CC8.1-07, CC4.1-05
| Select and connect the HRIS — unblocks the joiner, mover and leaver population | Security Officer | Not started | 7 | 9 |  |  | CC6.2-03, CC6.2-04
| Agent inventory, dedicated identities, promptfoo and garak in CI | Security Officer | Not started | 9 | 12 |  |  | CC6.3-04, CC7.1-04, CC7.2-04
WS4 | Evidence and operating cadence — Start the cycles that produce retained evidence, and keep them running. | Security Officer | Not started | 6 | 18 |  |  | Retires: GOV-003, GOV-004
| Control matrix with owner, frequency, risk, objective and control type | Security Officer | Not started | 5 | 6 |  |  | CC1.5-03, CC5.1-02, CC5.1-04
| Compliance calendar wired to the plan of action so a missed date becomes a deficiency | Security Officer | Not started | 6 | 7 |  |  | CC4.2-06, CC5.3-04
| Monthly cycle — scanning, alert disposition note, finding triage | Security Officer | Not started | 7 | 18 |  |  | CC4.1-03, CC4.1-04, CC7.3-03
| Quarterly cycle — access reviews, change population review, Committee report | Security Officer | Not started | 10 | 18 |  |  | CC4.1-02, CC4.1-05, CC2.2-05, CC4.2-02
| First control self-assessment, signed by the CEO | Security Officer | Not started | 11 | 13 |  |  | CC4.1-01, CC1.2-04, CC1.3-05
| Second monthly and quarterly cycles — the point at which the trail is real | Security Officer | Not started | 14 | 18 |  |  | CC4.2-05, CC7.5-03
WS5 | People and governance — Close the CC1 gaps, which are 21 of the 47 open items and the weakest criterion in the plan. | CEO | Not started | 2 | 14 |  |  | Retires: HR-001, HR-002, GOV-001, GOV-002, BCP-001, IR-001
| Create security@ and ethics@ routing to the CEO; publish and brief them | CEO | Not started | 2 | 2 |  |  | CC1.1-04, CC2.2-04, CC2.2-06
| Organisation chart, role descriptions, competency statements | CEO | Not started | 3 | 4 |  |  | CC1.3-01, CC1.4-01
| STD-SCR-001 screening tiers and the contractor equivalence statement | CEO | Not started | 4 | 6 |  |  | CC1.1-06, CC1.4-06
| Governance Decisions Log in use; delegations and acceptances recorded | CEO | Not started | 6 | 8 |  |  | CC1.2-02, CC1.3-04, CC3.2-06
| Annual review form with security responsibilities; conduct process split defined | CEO | Not started | 8 | 10 |  |  | CC1.5-02, CC1.1-05, CC1.5-05
| Annual Control Environment Assessment drafted and signed — independence, segregation, override | CEO | Not started | 11 | 14 |  |  | CC1.2-04, CC1.2-06, CC3.3-03
WS6 | Customer-facing commitments — Make the six commitments in POL-ISP-001 §9 real before a customer relies on one. | CEO | Not started | 2 | 10 |  |  | Retires: CMP-001, CMP-002, CMP-003, TPR-001
| Establish whether POL-PRIV-001 exists; bring it under control or remove the references | CEO | Not started | 2 | 2 |  |  | CC2.3-03, CC2.3-04
| Publish the security contact externally with security.txt | CEO | Not started | 2 | 3 |  |  | CC2.3-02
| Customer commitments register — every promise and the control that delivers it | CEO | Not started | 3 | 5 |  |  | CC2.3-01
| Sub-processor list derived from the vendor inventory, with a notification step | CEO | Not started | 4 | 6 |  |  | CC2.3-03, CC9.2-01
| Security Officer review gate at engagement intake before any commitment is given | CEO | Not started | 5 | 7 |  |  | CC2.3-05
| Complementary user entity controls stated; AWS assurance review performed | CEO | Not started | 7 | 10 |  |  | CC2.3-06, CC4.1-07, CC9.2-03
WS7 | Audit and assurance — Get to a Type I opinion, then run a clean observation window to a Type II. | CEO | Not started | 13 | 52 |  |  | Retires: GOV-004
| Readiness review — every control at 2 or above, gaps closed or accepted in writing | CEO | Not started | 12 | 14 |  |  | —
| Select the service auditor; agree scope, system description and carve-out | CEO | Not started | 13 | 15 |  |  | —
| Independent penetration test, after the free scanners have cleared the easy findings | CEO | Not started | 15 | 18 |  |  | CC4.1-03
| Type I fieldwork and management assertion | CEO | Not started | 18 | 21 |  |  | —
| Observation window opens — a minimum of six months | CEO | Not started | 22 | 22 |  |  | —
| Type II fieldwork against the window | CEO | Not started | 48 | 52 |  |  | —
MILESTONES | A milestone is a condition, not a date. If the gate is not met the date moves.
M1 | Quick wins closed |  |  | 2 | 2 |  |  | gitleaks live, both mailboxes routing, POL-PRIV-001 question answered |  |  | ◆
M2 | Library reissued at v1.1 |  |  | 6 | 6 |  |  | All 42 edits made, 21 tables of contents refreshed, seven cross-references corrected | [6 empty] | ◆
M3 | Tooling live |  |  | 9 | 9 |  |  | Logging, GuardDuty, Kandji, GitHub Enterprise, scanners — evidence begins accumulating | [9 empty] | ◆
M4 | First assessment signed |  |  | 13 | 13 |  |  | Risk assessment and control self-assessment complete, CEO signature on both | [13 empty] | ◆
M5 | Every control at 2 or above |  |  | 16 | 16 |  |  | The Type I bar. Anything still at 0 or 1 is accepted in writing or it blocks | [16 empty] | ◆
M6 | Type I opinion |  |  | 21 | 21 |  |  | Design tested and reported | [21 empty] | ◆
M7 | Observation window opens |  |  | 22 | 22 |  |  | Six months minimum. Cadence discipline from here decides the Type II | [22 empty] | ◆
M8 | Window closes |  |  | 48 | 48 |  |  | Two quarterly cycles and six monthly cycles evidenced | [48 empty] | ◆
M9 | Type II fieldwork |  |  | 52 | 52 |  |  | Operating effectiveness tested across the window | [52 empty] | ◆
BAR COLOURS | Set Status in column D and the bar recolours automatically. | [9 empty] | Not started |  |  | In progress |  |  | Blocked |  |  | Done

## Milestones
Milestones and their gates
A milestone is a condition, not a date. If the gate is not met, the date moves rather than the standard.
ID | Week | Milestone | Gate — what must be true
M1 | 2 | Quick wins closed | gitleaks live, both mailboxes routing, POL-PRIV-001 question answered
M2 | 6 | Library reissued at v1.1 | All 42 edits made, 21 tables of contents refreshed, seven cross-references corrected
M3 | 9 | Tooling live | Logging, GuardDuty, Kandji, GitHub Enterprise, scanners — evidence begins accumulating
M4 | 13 | First assessment signed | Risk assessment and control self-assessment complete, CEO signature on both
M5 | 16 | Every control at 2 or above | The Type I bar. Anything still at 0 or 1 is accepted in writing or it blocks
M6 | 21 | Type I opinion | Design tested and reported
M7 | 22 | Observation window opens | Six months minimum. Cadence discipline from here decides the Type II
M8 | 48 | Window closes | Two quarterly cycles and six monthly cycles evidenced
M9 | 52 | Type II fieldwork | Operating effectiveness tested across the window

## Blockers
Blockers to clear first
Each of these stops work that cannot start without it. They are sequenced early in the roadmap for that reason.
Blocker | What it stops | Where it is handled | Owner
HRIS not selected | Blocks CC6.2-04 and CC6.8-01 — revocation timeliness and endpoint coverage cannot be evidenced without an authoritative personnel population | WS3 W7–9 | Security Officer
GitHub Team plan | Branch protection on private repositories needs Enterprise. Blocks CC8.1-04, CC4.1-05 and CC5.2-04 | WS3 W5–7 | Security Officer
Deficiency destination undecided | Five policies name five different homes. Blocks a producible deficiency population, so CC4.2 cannot be tested | WS1 W1–2 | Security Officer
POL-PRIV-001 status unknown | Two customer-facing controls depend on a document not in the library | WS6 W2 | CEO
FRM-CE-001 does not exist | Four CC1 and CC3 controls reference it as their evidence artifact | WS5 W11–14 | CEO
Incident role model assumes 15–20 people | POL-IRP-001 §6 cannot be staffed at current headcount; needs external parties named or a recorded limitation | WS1 W4–6 | CEO

## Capacity
Capacity — the constraint that decides whether the plan holds
Tooling shrinks the automated column. It does not shrink the manual one. At two people the risk is not the Type I, it is sustaining cadence across a six-month observation window.
Mode | Controls | What it means
Automated | 115 | Runs without a person once configured. WS3 is the whole of this.
Semi-automated | 11 | System-assisted; a person still acts. Mostly ticket-driven.
Manual | 34 | Performed by a person. This is the number that headcount limits, and it does not shrink with tooling.
Continuous | 38 | Controls that run all the time. Configuration plus a periodic disposition review.
Quarterly | 21 | Access reviews, change population review, Committee report.
Annual | 60 | The easy majority — but they cluster around the annual assessment.
Event-driven | 38 | Fire on a trigger rather than a date. Intake is where most of them are met.